## Schedule
Master's Thesis: Extending Idefix package
[7 empty] | Period Highlight: | 1 |  |  | Plan | [6 empty] | Actual |  |  |  |  | % Complete | [5 empty] | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | DESCRIPTION | PRODUCT | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
 | time axis 2018-09-10 to 2019-07-08
 | time axis 2018-09-10 to 2019-07-08
Research plan | Set research plan | Update schedule | 1 | 3 | 0 | 0 | 0%
Literature study | Literature review needed to hand in the first summary. Deadline: 19-11-2018 | Summary for Lstat | 1 | 12 | 0 | 0 | 0%
Discrete Choice | Get familiar with these models: Read papers sent by Frits, books he borrowed me and other material found online. References: 2,3,7,8 | Update review matrix | 1 | 12 | 0 | 0 | 0%
GitHub | Know how: Learn how to properly use it in Rstudio. Working with other people is the challenge. | Create account, create easy projects, share code, copy idefix folder from Frits GitHub. Update review matrix | 1 | 2 | 0 | 0 | 0%
Advanced R | Know how: efficient programming in R. Speed algorithms in C++, java, etc. References: 9,10,11,12 | Update review matrix, create several example scripts showing a comparison of speed processing. Update review matrix | 3 | 10 | 0 | 0 | 0%
Shiny | Know how: Learn how to properly use Shiny at its maximum | Create different examples of shiny apps. Update review matrix | 3 | 3 | 0 | 0 | 0%
Review of summary | Final version of summary | Review from prof. Martina. Apply changes and modifications | 11 | 2 | 0 | 0 | 0%
First draft of thesis | Create document, give preliminar structure | Take template from webpage. Give structure. If possible add some comments | 13 | 1 | 0 | 0 | 0%
Update Schedule | Update Schedule | Update Schedule | 13 | 1 | 0 | 0 | 0%
Explore code idefix | Go trough all lines of code and understand each function | Own comments in scripts, possibly comments in GitHub. Update review matrix | 14 | 10 | 0 | 0 | 0%
Read documentation | Documentation on CRAN, maybe scripts that are not published from Frits | Update review matrix | 14 | 2 | 0 | 0 | 0%
Go through | See in detail all functions in the package | Own comments in scripts, possibly comments in GitHub. | 16 | 8 | 0 | 0 | 0%
Share findings | Share findings and ideas with Frits and prof. Martina | Discuss about new improvements, new functions | 24 | 1 | 0 | 0 | 0%
Prepare presentation | Prepare first presentation | slides. Summary, what have happened, what's left to be done | 24 | 5 | 0 | 0 | 0%
Update Schedule | Update Schedule | Update Schedule | 28 | 1 | 0 | 0 | 0%
New developments | New functions, new algorithms | New scripts, comparison between old and new functions.New functions, new algorithms | 25 | 10 | 0 | 0 | 0%
Speed up proccess | Speed up functions in R and Cpp or others | New scripts, comparison between old and new functions | 25 | 6 | 0 | 0 | 0%
New functions | Develop new functions, implement new algorithms | New functions, new algorithms | 30 | 5 | 0 | 0 | 0%
Documentation process | Comment and document all new developments done in the package | Updated documentation | 28 | 7 | 0 | 0 | 0%
Thesis | Different versions, writing each process | New versions of the document | 22 | 17 | 0 | 0 | 0%
Second draft |  |  | 31 | 1 | 0 | 0 | 0%
Third draft |  |  | 35 | 1 | 0 | 0 | 0%
Defence | Prepare defence | Slides | 39 | 4 | 0 | 0 | 0%
Actividad 22 |  |  | 14 | 7 | 14 | 3 | 0%
Actividad 23 |  |  | 15 | 4 | 15 | 8 | 12%
Actividad 24 |  |  | 15 | 5 | 15 | 3 | 5%
Actividad 25 |  |  | 15 | 8 | 15 | 5 | 0%
Actividad 26 |  |  | 16 | 28 | 16 | 30 | 50%